## Summary
Project Planner Guide
Sheet Project Information: | Hiện thị thông tin Project
Sheet Project Function: | Hiển thị lịch phân công tổng quan theo các chức năng
Note Details: | Giải thích những chức năng, thảo luận…
Trong mỗi Sheet: | Activities = | Tên công việc / chức năng sẽ thực hiện (copy từ checklist có kèm mã thứ tự) | Lưu ý: | - Không làm thay đổi format của mỗi sheet
| Member = | Tên của thành viên được phân công |  | - Nếu cần thì chèn dòng / cột vào giữa các dòng / cột có sẵn
| Plan start = | Số thứ tự Ngày dự kiến bắt đầu (tính theo ngày bắt đầu dự án) |  | - Phần ngày tháng trên plan (hiển thị theo d/m. Nhưng nhập theo m/d)
| Plan duration = | Số lượng ngày dự kiến hoàn thành công việc
| Actual start = | Số thứ tự Ngày thực sự bắt đầu (tính theo ngày bắt đầu dự án)
| Actual duration = | Số lượng ngày thực sự hoàn thành công việc
| Percent complete = | Phần trăm đánh giá của Cá nhân cho công việc. Mặc định công việc chưa hoàn thành thì ghi 0%

## PROJINFO
Project Information
Team Name:
| Member List: | STUDENT ID | FULL NAME | EMAIL | PHONE NUMBER | % CONTRIBUTION | NUMBER OF GIT COMMITS
|  | 1912 | Phan Huy Hoàng | 19127409@student.hcmus.edu.vn | 0355509301 | 30% (11 Function ) | 1
|  | 1912 | Lê Hoàng Thịnh Phước | 19127518@student.hcmus.edu.vn | 0945093057 | 38% ( 15 Funciton ) | 10
|  | 1912 | Nguyễn Minh Kha | 19127428@student.hcmus.edu.vn | 0973597990 | 32% (12 Function ) | 64
| Project ID: | CS162-KTLT Final Project |  | Start Project Date: | 2020-04-20
| Project Name: | Student Management System |  | End Project Date: | Friday, June 20, 2020
Requirements
Menu
Data must be stored in file. You can define your own format but it must store all the information as described above.
Be sure that, if I delete a csv file after importing, there is no harm to your system.
Hash password (optional). Tip: SHA1, SHA256…
Dùng mảng động, không dùng vector
Tổng % Contribution của các thành viên, ko được vượt quá 100%
% Contribution của các thành viên ko được đều nhau

## PROJFUNCTIONS
Project Planner & Evaluation
[10 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
[5 empty] | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01
CODE | ACTIVITY | COST | MARK SCHEME | STUDENT SELF-EVALUATION!!! | START | DURATION | START | DURATION | COMPLETE | PERIODS
|  | (*USD) |  |  | (day) | (count) | (day) | (count) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
1 | All roles |  | 5 | 0
1.1 | Login |  | 1 |  | 2 | 2 | 2 | 2 | 100%
1.2 | Show menu |  | 1 |  | 4 | 2 | 4 | 2 | 20%
1.3 | View profile info |  | 1 |  | 3 | 2 | 3 | 2 | 10%
1.4 | Change password |  | 1 |  | 9 | 3 | 9 | 3
1.5 | Logout |  | 1
2 | Academic staff-Class |  | 9 | 0
2.1 | *Import students of a class such as 18CLC6 from a csv file. |  | 3
2.2 | Manually add a new student to a class. |  | 1
2.3 | Edit an existing student. |  | 1
2.4 | Remove a student. |  | 1
2.5 | Change students from class A to class B |  | 1
2.6 | View list of classes. |  | 1
2.7 | View list of students in a class. |  | 1
3 | Academic staff-Courrse |  | 13 | 0
3.1 | Create / update / delete / view academic years (2018-2019), and semesters (Fall). |  | 1
3.2 | *From a semester, import courses such as CTT008, CTT010 from a csv file. |  | 3
3.3 | Manually add a new course. |  | 1
3.4 | Edit an existing course. |  | 1
3.5 | Remove a course. |  | 1
3.6 | Remove a specific student from a course. |  | 1
3.7 | Add a specific student to a course. |  | 1
3.8 | View list of courses in the current semester. |  | 1
3.9 | View list of students of a course. |  | 1
3.1 | View attendance list of a course. |  | 1
3.11 | Create / update / delete / view all lecturers. |  | 1
4 | Academic staff-Score board |  | 4 | 0
4.1 | Search and view the scoreboard of a course. |  | 1
4.2 | Export a scoreboard to a csv file. |  | 1
5 | Academic staff-Attendance list
5.1 | Search and view attendance list of a course. |  | 1
5.2 | Export a attendance list to a csv file. |  | 1
6 | Lecturer |  | 8 | 0
6.1 | View list of courses in the current semester. |  | 1
6.2 | View list of students of a course. |  | 1
6.3 | View attendance list of a course. |  | 1
6.4 | Edit an attendance. |  | 1
6.5 | *Import scoreboard of a course (midterm, final, lab, bonus) from a csv file. |  | 2
6.6 | Edit grade of a student |  | 1
6.7 | View a scoreboard |  | 1
7 | Student |  | 6 | 0
7.1 | *Check-in. |  | 3
7.2 | View check-in result. |  | 1
7.3 | View schedules. |  | 1
7.4 | View his/her scores of a course. |  | 1
| TỔNG ĐIỂM |  | 45 | 0
35 điểm tương đương 10 điểm
Ko có self-evaluation, 0đ
Ko login được, 0đ
Thiếu >=2 chức năng có dấu *, 0đ
Chức năng nào ko có data để demo, 0đ
Tất cả thành viên đều phải có mặt trong lúc vấn đáp
Đi trễ, mỗi lần gọi trừ 1/10 điểm, gọi quá 3 lần thì 0đ.
Plan Start là số thứ tự của ngày bắt đầu. Ví dụ bắt đàu từ ngày thứ 2 tức là ngày 7 Apr 202
Plan duration là làm trong bao nhiêu ngày…
…

## NoteDetails
Code | Activity | Description | Ghi chú
2.1 |  | The csv file should include columns such as No (1), Student ID (18125001), Lastname (Nguyen Van), Firstname (A), Gender (Male), DoB (2000-04-01)
Remember to create student accounts based on their Student ID and their DoB.
2.2 |  | For example, there is a new student enrolled in 18CLC6.
Remember to create a student account based on his/her Student ID and their DoB.
3.2 |  | The csv file should include columns such as No (1), Course ID (CTT008), Course Name (Programming Techniques), Class (18CLC6), LecturerAccount (nhminh), Start Date (2019-01-07), End Date (2019-04-13), Day of Week (Wed), Start Hour:Minute (08:00), and End Hour:Minute (11:00), Room (I33).
By default, all students in the mentioned classes will be enrolled to imported courses.
3.6 |  | For example, by default all students of 18CLC are enrolled in course CTT008, but because of a private reason, student Nguyen Van A is dropped from CTT008.
3.7 |  | For example, student 1753001 enrolls in CTT008 to improve his previous result.