## Summary
Project Planner Guide
Sheet Project Information: | Hiện thị thông tin Project
Sheet Project Function: | Hiển thị lịch phân công tổng quan theo các chức năng
Note Details: | Giải thích những chức năng, thảo luận…
Trong mỗi Sheet: | Activities = | Tên công việc / chức năng sẽ thực hiện (copy từ checklist có kèm mã thứ tự) | Lưu ý: | - Không làm thay đổi format của mỗi sheet
| Member = | Tên của thành viên được phân công |  | - Nếu cần thì chèn dòng / cột vào giữa các dòng / cột có sẵn
| Plan start = | Số thứ tự Ngày dự kiến bắt đầu (tính theo ngày bắt đầu dự án) |  | - Phần ngày tháng trên plan (hiển thị theo d/m. Nhưng nhập theo m/d)
| Plan duration = | Số lượng ngày dự kiến hoàn thành công việc
| Actual start = | Số thứ tự Ngày thực sự bắt đầu (tính theo ngày bắt đầu dự án)
| Actual duration = | Số lượng ngày thực sự hoàn thành công việc
| Percent complete = | Phần trăm đánh giá của Cá nhân cho công việc. Mặc định công việc chưa hoàn thành thì ghi 0%

## ProjInfo
Project Information
Team Name:
| Member List: | Name | Email | Slack username | Phone
|  | Minh Kha | 19127428@student.hcmus.edu.vn | nmkha | +84973597990
|  | Huy Hoàng | 19127409@student.hcmus.edu.vn | phhoang | +84355509301
|  | Thịnh Phước | 19127518@student.hcmus.edu.vn | lhtphuoc | 84945093057
| Project ID: | CS162FinalProject |  | Start Project Date: | 2020-04-06
| Project Name: | Student management system |  | End Project Date:
Requirements
Menu
Data must be stored in file. You can define your own format but it must store all the information as described above.
Be sure that, if I delete a csv file after importing, there is no harm to your system.
Hash password (optional). Tip: SHA1, SHA256…
Dùng mảng động, không dùng vector
Có thể dùng string thay vì char*

## ProjFunctions
Project Planner
[9 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  |  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01
Code | ACTIVITY | Cost | Member | START | DURATION | START | DURATION | COMPLETE | PERIODS
|  | (*USD) |  | (day) | (count) | (day) | (count) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
1 | All roles
1.1 | Login (3 role: Academic Staff, Lecturer, Student) |  | Kha | 2 | 2 | 2
1.2 | Show menu |  | Hoang | 2 | 3 | 2
1.3 | View profile info |  | Phuoc | 2 | 3 | 2
1.4 | Change password |  | Kha | 2 | 2 | 2
1.5 | Logout |  | Hoang | 2 | 2 | 2
2 | Academic staff-Class
2.1 | *Import students of a class such as 18CLC6 from a csv file.
2.2 | *Manually add a new student to a class.
2.3 | Edit an existing student.
2.4 | Remove a student.
2.5 | Change students from class A to class B
2.6 | View list of classes.
2.7 | View list of students in a class.
3 | Academic staff-Courrse
3.1 | Create / update / delete / view academic years (2018-2019), and semesters (Fall).
3.2 | *From a semester, import courses such as CTT008, CTT010 from a csv file.
3.3 | Manually add a new course.
3.4 | Edit an existing course.
3.5 | Remove a course.
3.6 | *Remove a specific student from a course.
3.7 | *Add a specific student to a course.
3.8 | View list of courses in the current semester.
3.9 | View list of students of a course.
3.1 | View attendance list of a course.
3.11 | Create / update / delete / view all lecturers.
4 | Academic staff-Score board
4.1 | Search and view the scoreboard of a course.
4.2 | Export a scoreboard to a csv file.
5 | Academic staff-Attendance list
5.1 | Search and view attendance list of a course.
5.2 | Export a attendance list to a csv file.
6 | Lecturer
6.1 | View list of courses in the current semester.
6.2 | View list of students of a course.
6.3 | View attendance list of a course.
6.4 | Edit an attendance.
6.5 | Import scoreboard of a course (midterm, final, lab, bonus) from a csv file.
6.6 | Edit grade of a student
6.7 | View a scoreboard
7 | Student
7.1 | *Check-in (1 tuần học/checkin 1 buổi) trong 11 tuần
7.2 | View check-in result.
7.3 | View schedules.
7.4 | View his/her scores of a course.
Plan Start là số thứ tự của ngày bắt đầu. Ví dụ bắt đàu từ ngày thứ 2 tức là ngày 7 Apr 202
Plan duration là làm trong bao nhiêu ngày…
…

## NoteDetails
Code | Activity | Description | Ghi chú
1.1 |  | Username, pass, fullname, level…
2.1 |  | The csv file should include columns such as No (1), Student ID (18125001), Lastname (Nguyen Van), Firstname (A), Gender (Male), DoB (2000-04-01)
Remember to create student accounts based on their Student ID and their DoB.
2.2 |  | For example, there is a new student enrolled in 18CLC6.
Remember to create a student account based on his/her Student ID and their DoB.
3.2 |  | The csv file should include columns such as No (1), Course ID (CTT008), Course Name (Programming Techniques), Class (18CLC6), LecturerAccount (nhminh), Start Date (2019-01-07), End Date (2019-04-13), Day of Week (Wed), Start Hour:Minute (08:00), and End Hour:Minute (11:00), Room (I33).
By default, all students in the mentioned classes will be enrolled to imported courses.
3.6 |  | For example, by default all students of 18CLC are enrolled in course CTT008, but because of a private reason, student Nguyen Van A is dropped from CTT008.
3.7 |  | For example, student 1753001 enrolls in CTT008 to improve his previous result.
7.1 |  | Sinh viên tự điểm danh, đúng khung giờ